## Communication Tools
Overview of communication activities
Method | Purpose | Circulation / Promotion
Information pack | Includes overview of Fit for the Future program and presents options for consideration. | Distributed to all residents as unaddressed mail.
Community survey | Seeks feedback from community on preferred option, as presented in the information pack. Determines preferred level of service delivery. Will inform decision of Council to prepare either an amalgamation proposal or an improvements proposal. | Referred to in information pack delivered to all residents. Promoted in Weekly Snippets, Howlong Grapevine, Facebook pages, Website. Hard copies made available in all Council offices and libraries.
Community information sessions | Inform the community on the Fit for the Future program and the options being considered. | Promoted in Weekly Snippets, Howlong Grapevine, Facebook pages, Website. Posters placed in all Council facilities and key community locations. Corowa - Civic Centre Howlong - Community Health Centre Mulwala - Civic Centre
Staff newsletters | Informs staff of process and position of the Council. | Distributed electronically to all indoor staff and hard copies to outdoor staff. Monthly publication.
Media releases
Media alerts

## Timeline
Fit for the Future - Communication Action Plan
WHAT | FEBRUARY | [27 empty] | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Schedule delivery of information pack to all residents
Obtain quotes and book printing of information pack
Book venues for community meetings
Prepare presentation / information for community meetings
Update in staff newsletter
Promotion of community meetings (and survey):
Snippets
Council website
Tourism Facebook
What's On in Howlong Facebook (contact administrator)
Posters in all Council facilities
Media release promoting engagement process
Finalise information pack and send to printer
Printing of information pack
Information pack to PO
Delivery of information pack
Information pack available on Council website
Complete survey design
Survey to go live
Hard copies of survey made available at all Council facilities
Promotion of survey:
Snippets
Media alert - radio and tv
Council website
Tourism Facebook
What's On in Howlong Facebook (contact administrator)
Howlong Grapevine (copy provided by 15 Feb)
Community meetings
Telephone surveys completed
Survey responses collated and report prepared for Council
Public exhibition period of proposal
Promotion of public exhibition period:
Snippets
Council website
Tourism Facebook
What's On in Howlong Facebook (contact administrator)
Howlong Grapevine (copy provided by 15 March)
Promote Special Council Meeting (23 June)
Snippets
Website
Howlong Grapevine (copy provided by 15 May)